## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD Panther - GROUP B
Design ERD |  | Name: Pham Nguyen Minh Dang |  |  | Name: Nguyen Huy Hoang |  |  | Name: Nguyen Tan Phat |  |  | Name: N/A |  |  | Name: Full Name Member 5 | N/A
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design | Desgin ERD | 30/11/2024 | 30/11/2024
|  | Refine ERD | 2024-01-12 | 2024-01-12 | Refine ERD | 2024-01-12 | 2024-01-12 | Refine ERD | 2024-01-12 | 2024-01-12
Design System Architecture for Level X Requirement RXY |  | Review ERD | 2024-02-12 | 2024-02-12 | Review ERD | 2024-02-12 | 2024-02-12 | Review ERD | 2024-02-12 | 2024-02-12
Refine System Architecture for Level X Requirement RXY | Architecture Design | Desgin Context Diagram | 2024-01-12 | 2024-01-12 | Design Authentication Component Diagram (FE) | 2024-01-12 | 2024-01-12 | Design User Component Diagram (BE) | 2024-01-12 | 2024-01-12
Review System Architecture for Level X Requirement RXY |  | Design Container Diagram | 2024-01-12 | 2024-01-12 | Design Admin Component Diagram (FE) | 2024-01-12 | 2024-01-12 | Design Admin Component Diagram (BE) | 2024-01-12 | 2024-01-12
|  | Design Authentication Component Diagram (BE) | 2024-01-12 | 2024-01-12 | Design Donor / Guest Component Diagram (FE) | 2024-01-12 | 2024-01-12 | Design Statistics Module Component Diagram (BE) | 2024-01-12 | 2024-01-12
Design UX/UI for Level X Requirement RXY |  | Review all Architect Diagrams | 2024-02-12 | 2024-02-12 | Design Charity Component Diagram (FE) | 2024-01-12 | 2024-01-12 | Review all Architect Diagrams | 2024-02-12 | 2024-02-12
Refine UX/UI for Level X Requirement RXY |  | Refind all Architect Diagrams | 2024-03-12 | 2024-03-12 | Review all Architect Diagrams | 2024-02-12 | 2024-02-12 | Refind all Architect Diagrams | 2024-03-12 | 2024-03-12
Review UX/UI for Level X Requirement RXY |  |  |  |  | Refind all Architect Diagrams | 2024-03-12 | 2024-03-12
HTML/CSS for Level X Requirement RXY
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Report: Introduction
Report: Project Background
Report: Conclusion
Report: EDR Design
Report: Architecture Design | Back-end Development
Report: Architecture Analysis
Report: Format Report
| Reporting | Report: Introduction | 2024-03-12 | 2024-03-12 | Report: Architecture Design | 2024-03-12 | 2024-03-12 | Report: Architecture Analysis | 2024-03-12 | 2024-03-12
|  | Report: Project Background | 2024-03-12 | 2024-03-12 | Report: Format Report | 2024-03-12 | 2024-03-12 | Report: Format Report | 2024-03-12 | 2024-03-12
|  | Report: Conclusion | 2024-03-12 | 2024-03-12
|  | Report: EDR Design | 2024-03-12 | 2024-03-12