## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD [ID] - GROUP [A OR B]
Design ERD |  | Name: Hur Hyeon Bin |  |  | Name: Bui Hong Thanh Thien |  |  | Name: Tran Vinh Trong |  |  | Name: Vo Duc Tan |  |  | Name: Tran Thanh Tu
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
|  | Design ERD (Implement ERD prototype) | 20/11/2024 | 20/11/2024
Review ERD | ERD Design | Design ERD (Implement ERD prototype with Charity, Charity Project, Admin, Admin Action) | 20/11/2024 | 20/11/2024 | Add the entity in Charity and transaction tables, create the table for emai, interest, subscription and project shard on draw.io. | 2024-01-12 | 2024-01-12 | Review ERD. | 2024-01-12 | 2024-01-12 | Review ERD | 2024-01-12 | 2024-01-12 | Review ERD | 2024-01-12 | 2024-01-12
|  | Refine ERD (Add Subscription, Interest, Email, Charity Project Shard ) | 2024-01-12 | 2024-01-12 | Review ERD | 2024-01-12 | 2024-01-12
Design System Architecture for Level X Requirement RXY |  | Review ERD | 2024-01-12 | 2024-01-12
Refine System Architecture for Level X Requirement RXY | Architecture Design | Design Container Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 22/11/2024 | 2024-01-12 | Design the draft for back-end component diagram level 1 | 22/11/2024 | 22/11/2024 | Review Container Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 2024-01-12 | 2024-01-12 | Finalize and add the design for Back-end component diagram | 2024-01-12 | 2024-01-12 | Review the frontend component diagram All level | 2024-01-12 | 2024-01-12
Review System Architecture for Level X Requirement RXY |  | Refine Container Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 24/11/2024 | 2024-01-12 | Design the draft for back-end component diagram level 2 | 22/11/2024 | 22/11/2024 | Design Container Diagram for Level 2 Draft | 24/11/2024 | 24/11/2024 | Review the container diagram for all Level | 2024-01-12 | 2024-01-12 | Review the backend container diagram all level | 2024-01-12 | 2024-01-12
|  | Review Container Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 24/11/2024 | 2024-01-12 | Design the draft for back-end component diagram level 3 | 22/11/2024 | 22/11/2024 | Review Container Diagram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 2024-01-12 | 2024-01-12 | Review the front-end component diagram for Level 1 | 2024-01-12 | 2024-01-12 | Review the backend component diagram all level | 2024-01-12 | 2024-01-12
Design UX/UI for Level X Requirement RXY |  | Design Container Diagram for Level 2All Requirements (2A.1.2 to 2A.2.4) | 22/11/2024 | 2024-01-12 | Refine the back-end component diagram for all Level | 28/11/2024 | 28/11/2024 | Design Front End Component Diagram for Level 1 Draft | 24/11/2024 | 24/11/2024 | Review the front-end component diagram for Level 2 | 2024-01-12 | 2024-01-12 | Finalize backend component diagram | 2024-01-12 | 2024-01-12
Refine UX/UI for Level X Requirement RXY |  | Refine Container Diagram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 24/11/2024 | 2024-01-12 | Review the container diagram for all Level | 24/11/2024 | 24/11/2024 | Review Front End Component Digaram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 2024-01-12 | 2024-01-12 | Review the front-end component diagram for Level 3 | 2024-01-12 | 2024-01-12 | Design backend component diagram for level 3 | 30/11/2024 | 30/12/2024
Review UX/UI for Level X Requirement RXY |  | Review Container Diagram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 24/11/2024 | 2024-01-12 | Review the all front-end component diagrams for Level 1 | 2024-01-12 | 2024-02-12 | Review Front End Component Digaram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 24/11/2024 | 24/11/2024 | Review the back-end component diagram for Level 1 | 2024-01-12 | 2024-01-12 | Design backend component diagram for level 2 | 30/12/2024 | 30/12/2024
|  | Design Container Diagram for Level 3 All Requirements (3A.1.1 to 3A.4) | 22/11/2024 | 2024-01-12 | Review the all front-end component diagrams for Level 2 | 2024-01-12 | 2024-02-12 | Design Front End Component Digaram for Level 2 Draft | 24/11/2024 | 24/11/2024 | Review the back-end component diagram for Level 2 | 2024-01-12 | 2024-01-12 | Redesign backend component diagram for level 1 | 30/12/2024 | 30/12/2024
HTML/CSS for Level X Requirement RXY |  | Refine Container Diagram for Level 3 All Requirements (3A.1.1 to 3A.4) | 24/11/2024 | 2024-01-12 | Review the all front-end component diagrams for Level 3 | 2024-01-12 | 2024-02-12 | Review Front End Component Digaram for Level 3 All Requirements (3A.1.1 to 3A.4) | 2024-01-12 | 2024-01-12 | Review the back-end component diagram for Level 3 | 2024-01-12 | 2024-01-12
|  | Review Container Diagram for Level 2 All Requirements (3A.1.1 to 3A.4) | 24/11/2024 | 2024-01-12 |  |  |  | Review Back End Component Digaram for Level 3 All Requirements (3A.1.1 to 3A.4) | 2024-01-12 | 2024-02-12
|  | Design Front End Component Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 29/11/2024 | 2024-02-12 |  |  |  | Review Back End Component Digaram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 2024-01-12 | 2024-02-12
|  | Refine Front End Component Diagram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 30/11/2024 | 2024-02-12
|  | Review Front End Component Digaram for Level 1 All Requirements (1A.1.1 to 1A2.5) | 2024-01-12 | 2024-02-12
|  | Design Front End Component Diagram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 29/11/2024 | 2024-02-12
|  | Refine Front End Component Diagram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 30/11/2024 | 2024-02-12
|  | Review Front End Component Digaram for Level 2 All Requirements (2A.1.2 to 2A.2.4) | 2024-01-12 | 2024-02-12
|  | Design Front End Component Diagram for Level 3 All Requirements (3A.1.1 to 3A.4) | 29/11/2024 | 2024-02-12
|  | Refine Front End Component Diagram for Level 3 All Requirements (3A.1.1 to 3A.4) | 30/11/2024 | 2024-02-12
|  | Review Front End Component Digaram for Level 3 All Requirements (3A.1.1 to 3A.4) | 2024-01-12 | 2024-02-12
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Back-end Development
| Reporting | System Architecture - Overall System Architecture | 2024-01-12 | 2024-02-12 | ERD explanation on the report | 2024-01-12 | 2024-01-12 | Back End Architecture explanation on components and containers | 2024-01-12 | 2024-01-12 | Introduction & Project Background Information | 2024-01-12 | 2024-01-12 | Extensibility, Resilience, Scalability in Architecture Analysis | 2024-02-12 | 2024-02-12
|  | System Architecture - Front End Architecture | 2024-01-12 | 2024-02-12 | Conclusion | 2024-01-12 | 2024-01-12 | Formating the report | 2024-01-12 | 2024-01-12 | Maintainability, Security & Performance in Architecture Analysis | 2024-01-12 | 2024-01-12 | Formating the report | 2024-03-12 | 2024-03-12
[8 empty] | Conclusion | 2024-01-12 | 2024-01-12 | Creating report template | 2024-09-11 | 2024-09-11
[11 empty] | Conclusion | 2024-01-12 | 2024-01-12